## 270718
# | Activities planned for today | Testing Type | Personnel | Status at EOD
1 | File uploading scenario scripting in-progress | Performance | Martin | Stuck in parameterization due to mismatch in token or extraction error
2 | Confirmed eway bill generate scenario. | Performance | Aarya | Scenario confirmed after confirmation from Praveen "Despite validation issues being existent on available Data pointers, we can go ahead and use those scenarios for generate as creating the server load and measuring the system performance at that time is our main agenda"
3 | Eway bill Generate scenario to be recorded. | Performance | Aarya | Done
4 | Tweak the TestNG framework as per inputs received from onsite team | Functional | Jerrin | Ritesh/Praveen couldn't take the review of the same, review rescheduled for 10.30 am on 30/07/18
5 | Login Module scripting to be done as per Test Plan | Functional | Jerrin | Done (Yet to be reviewed)

## 300718
# | Activities planned for today | Testing Type | Personnel | Testing Type | Personnel | Status at EOD
[6 empty] | What I accomplished today | What I will be working on tomorrow
1 | Generate Scenario | Performance | Martin | Performance | Martin | Scripting In progress.Completed extracting grid values using json extractor. | Response json to be updated.Need to validate in UI.
2 | All EWB page | Performance | Silpa | Regression | Shilpa | Recording completed.Scripting in progress and token extraction in progress | Scripting will be completed.
3 | Ensure that Generate, Login and All EWB page script can be run on continuously loop and is being parameterized | Performance | Anoop | Performance | Anoop | Parameterization In progress | Parameterization for generate and All EWB to be checked
4 | Create 100 users for Load testing from backend with User login ID format as load_testing_<number> | Performance | Praveen/Prabhakar | Performance | Praveen/Prabhakar | Request passed on to development team . Expecting to get it done by today EOD | Praveen to send username and encrypted passwords
5 | Finalize the reporting parameters and the responsible personnel/tool for the same | Performance | Anoop/Prabhakar | Performance | Anoop/Prabhakar | Prabhakar to share the list of reporting parameters that would be extracted from server | Praveen to follow up with Prabhakar and get the list of reporting parameters from server side
6 | Generate EWB (1-10 scenarios) | Regression | Aarya | Regression | Aarya | Few errors occurred in login scenario were rectified. | Start with 1 scenario
8 | Generate EWB (20-25 scenarios) | Regression | Jerin | Regression | Jerrin | Generate EWB in progress. Issue faced in picking up data from grid | Complete generate scenario.Praveen to send automated scenarios.
9 | Data Upload | Regression | Rajneesh |  |  | Scripting for Data upload completed. Invalid file name error faced | Feedback received on the error.Will be working on the same and moving on to next scenario

## 310718
# | Activities planned for today | Testing Type | Personnel | Testing Type | Personnel | Status at EOD
[6 empty] | What I accomplished today | What I will be working on tomorrow
1 | Generate Scenario- Response json to be updated.Need to validate in UI. | Performance | Martin | Performance | Martin | Generate Scenario-90% completed.Verified in UI with some variables | Collaborated scenario of Data upload and Generate EWB
2 | All EWB page- Scripting and token extraction to be completed. | Performance | Silpa | Regression | Shilpa | All EWB Scripting completed.Login logout scenario is executed with 4 virtual users | Parameterisation of login and logout and All EWB
3 | Ensure that Generate, Login and All EWB page script can be run on continuously loop and is being parameterized- Parameterization for generate and All EWB to be checked | Performance | Anoop | Performance | Anoop | Paramerisation for Generate completed | All EWB to be checked
4 | Create 100 users for Load testing from backend with User login ID format as load_testing_<number> | Performance | Praveen/Prabhakar | Performance | Praveen/Prabhakar | While checking, reset password pop-up was appearing.Users has been asked toremove reset password screen. | Reset Password screen is removed . To be teasted again
5 | Finalize the reporting parameters and the responsible personnel/tool for the same | Performance | Anoop/Prabhakar | Performance | Anoop/Prabhakar | Discussions and finalisation of the same | Will circulate the final report
6 | Generate EWB (1-10 scenarios) | Regression | Aarya | Regression | Aarya | Completed All EWB positive Scenario | Start a new scenario from All EWB
8 | Generate EWB (20-25 scenarios)-Complete generate scenario | Regression | Jerin | Regression | Jerrin | Completed Generate EWB Scenario | Two or more Autamatable scenario from 20 to 25
9 | Data Upload- Working on the error with the feedback received and moving on to next scenario | Regression | Rajneesh |  |  | Leave | Feedback received on the error.Will be working on the same and moving on to next scenario

## 010818
# | Activities planned for today | Testing Type | Personnel | Testing Type | Personnel | Status at EOD
[6 empty] | What I accomplished today | What I will be working on tomorrow
1 | Generate Scenario- Collaborated scenario of Data upload and Generate EWB | Performance | Martin | Performance | Martin | Generate scenario verified with parameterized variables,Done some fine tuning collabaration of file upload and generate started. | Check impact of loading different set of files . Collaboration of upload and generate Inputs got based on the trial test run: 1. Instead of single 1000 record file, we need to check with 5 different set of files randomly with varying records for users. 2. Testing with gradually changing user load and finding the breakpoint. 3. Generate page with 50,000 records (Prerequisite: Development team have to bring down records to 50,000 )
2 | All EWB page- Parameterisation of login and logout and All EWB | Performance | Silpa | Regression | Shilpa | Parameterization of login logout and all ewb completed,set delay for all ewb,created csv file with new user credentials for test run;with the newly encrypted password. | Check impact of loading different set of files . Collaboration of upload and generate
3 | Ensure that Generate, Login and All EWB page script can be run on continuously loop and is being parameterized- All EWB to be checked | Performance | Anoop | Performance | Anoop | DONE
4 | Create 100 users for Load testing from backend with User login ID format as load_testing_<number>- Reset Password screen is removed . To be tested again | Performance | Praveen/Prabhakar | Performance | Praveen/Prabhakar | Confirmed
5 | Finalize the reporting parameters and the responsible personnel/tool for the same-Circulate the final report | Performance | Anoop/Prabhakar | Performance | Anoop/Prabhakar | Confirmed
6 | Generate EWB (1-10 scenarios) - Start a new scenario from All EWB | Regression | Aarya | Regression | Aarya | ALL EWB_07 - Cancelation scenario 70% completed Input after meeting: Need to check NIC status also. | Completing ALL EWB_07 with NIC status check. ALL EWB_06- Updation of NIC status based on the changes made in Update vehicle page
8 | Generate EWB (20-25 scenarios)-Two or more Autamatable scenario from 20 to 25 | Regression | Jerin | Regression | Jerrin | Completed excluded scenario | Scenario from "EWB Extend"
9 | Data Upload- Working on the error with the feedback received and moving on to next scenario | Regression | Rajneesh |  |  | Completed Data upload DU_01 to DU_05 Error in uploading part. Error sorted out. | Data Upload DU_06 to DU_10

## 020818
# | Activities planned for today | Testing Type | Personnel | Testing Type | Personnel | Status at EOD
[6 empty] | What I accomplished today | What I will be working on tomorrow
1 | Generate Scenario- Collaborated scenario of Data upload and Generate EWB Load testing scenarios . 1. Static 1000 set of records not to be used for data upload, instead we use different combinations for number of records in the upload file. The decided record sets are 50, 100, 300, 500, 1000 2. We should be able to provide page level response time at different user loads to understand that a page loads at x seconds at 1 user load, and y seconds at 10 user loads. The decided user load sets are 1, 5, 10, 20, 40, 60, 80, 100 3. For starters, on an average there should be around 50,000 records on the generate page while testing. | Performance | Martin & Silpa | Performance | Martin | 1.Did correction in generate script inorder to extract records with NIC status=null and validation status =success 2. Created test data for test run 3. Test plan with file upload and generate scenario done | 1. Need to club all scenarios together 2. Need to prepare test data
2 | Generate EWB (1-10 scenarios) - Complete ALL EWB_07 with NIC status check. ALL EWB_06- Updation of NIC status based on the changes made in Update vehicle page | Regression | Aarya | Regression | Aarya | ALL EWB_07-Cancel-Inprogress,Update Vechicle-Inprogress | Complete ALL EWB_07-Cancel and Update Vechicle
3 | Generate EWB (20-25 scenarios)- Scenario from "EWB Extend" | Regression | Jerin | Regression | Jerrin | Leave | Scenario from "EWB Extend"
4 | Data Upload- Data Upload DU_06 to DU_10 | Regression | Rajneesh |  |  | DU_06, 07,08,09,10 has been completed | DU_10 to 18

## 030818
# | Activities planned for today | Testing Type | Personnel | Testing Type | Personnel | Status at EOD
[6 empty] | What I accomplished today | What I will be working on tomorrow
1 | Generate Scenario- Collaborated scenario of Data upload and Generate EWB Load testing scenarios . 1. Static 1000 set of records not to be used for data upload, instead we use different combinations for number of records in the upload file. The decided record sets are 50, 100, 300, 500, 1000 2. We should be able to provide page level response time at different user loads to understand that a page loads at x seconds at 1 user load, and y seconds at 10 user loads. The decided user load sets are 1, 5, 10, 20, 40, 60, 80, 100 3. For starters, on an average there should be around 50,000 records on the generate page while testing. 1. Need to club all scenarios together 2. Need to prepare test data | Performance | Martin & Silpa | Performance | Martin | 1. Extracted and created test data for generate scenario 2.Test executed with file upload and generate scenario executed. 3. User loads provided gradually as discussed 4. Done analysis and collaboration of execution details. | 1. Need to prepare a full plan combining all 4 scenarios 2. Need to create required test data before test run
2 | Generate EWB (1-10 scenarios) - Complete ALL EWB_07-Cancel and Update Vechicle | Regression | Aarya | Regression | Aarya | Completed ALLEWB_07-Cancel and ALLEWB_06 UpdateVehicle Functionality Issues found during testing All EWB Cancel/Update 1. Cancelled EWB can again be cancelled. 2. Cancelled EWB can be updated and saved again ie. Update Vehicle option is working for a cancelled EWB 3. Fields are not getting cleared while changing the mode of transport. | All EWB_08- Update movement page
3 | Generate EWB (20-25 scenarios)- Scenario from "EWB Extend" | Regression | Jerin | Regression | Jerrin | Generate_20-(Inprogress-80%Completed) Generate_23-(Completed) | Complete Generate_20
4 | Data Upload- DU_10 to 18 | Regression | Rajneesh |  |  | DU_10-15 has been completed Issue: When user moves to generate page then page not getting responding and then "Warning Unresponsive.." message is showing.` | DU_15 to 18

## 060818
# | Activities planned for today | Testing Type | Personnel | Testing Type | Personnel | Status at EOD
[6 empty] | What I accomplished today | What I will be working on tomorrow
1 | Generate Scenario- Collaborated scenario of Data upload and Generate EWB Load testing scenarios . 1. Need to prepare a full plan combining all 4 scenarios 2. Need to create required test data before test run | Performance | Martin & Silpa | Performance | Martin | Test Scripts for file upload , generate and All EWB Combined | Need to run combined test plan and analyse the results
2 | Generate EWB (1-10 scenarios) - All EWB_08- Update movement page | Regression | Aarya | Regression | Aarya | All EWB_08- Update movement page in progress | All EWB_08- Update movement page to be completed
3 | Generate EWB (20-25 scenarios)- Complete Generate_20 | Regression | Jerin | Regression | Jerrin | Page Response time scripting in progress | Page Response time scripting to be completed
4 | Data Upload- Admin - | Regression | Rajneesh |  |  | Completed Add company in ADMIN | Business Unit and Sub Business unit to be completed

## 070818
# | Activities planned for today | Testing Type | Personnel | Testing Type | Personnel | Status at EOD
[6 empty] | What I accomplished today | What I will be working on tomorrow
1 | Generate Scenario- Collaborated scenario of Data upload and Generate EWB Load testing scenarios . Need to run combined test plan and analyse the results | Performance | Martin & Silpa | Performance | Martin | Rearranged test data received from Prabhakar. Test combining file upload, generate and all EWB executed for 99(33 each) users for 30 mnts. Collected test execution details | Need to send report
2 | Generate EWB (1-10 scenarios) - All EWB_08- Update movement page to be completed | Regression | Aarya | Regression | Aarya | All EWB_08- Update movement :Completed Update vehicle_03- update vehicle with blank values :Completed | Update vehicle_02 - update vehicle with invalid values in the fields.
3 | Generate EWB (20-25 scenarios)- ON hold Page Response time scripting to be completed | Regression | Jerin | Regression | Jerrin | Page Response time scripting : Completed | Generate EWB (23,24,25 scenarios)
4 | Complete "Business Unit", "Sub-Busi Unit" section. | Regression | Rajneesh |  |  | Completed "Business Unit" , shared and discussed of my designed framework. | Will complete "Sub-Busi Unit" and "Location"

## 080818
# | Activities planned for today | Testing Type | Personnel | Testing Type | Personnel | Status at EOD
[6 empty] | What I accomplished today | What I will be working on tomorrow
1 | Generate Scenario- Collaborated scenario of Data upload and Generate EWB Load testing scenarios . Need to run combined test plan and analyse the results Need to send report | Performance | Martin & Silpa | Performance | Martin | Analysed the details and prepared test report Uploaded data for 2nd test run | Need to arrange test data Need to execute test run2 Analyse and send report.
2 | Generate EWB (1-10 scenarios) - Update vehicle_02 - update vehicle with invalid values in the fields. | Regression | Aarya | Regression | Aarya | Update vehicle_02 - update vehicle with invalid values in the fields : Completed | TRA_1:On first time login user should be prompted to reset password
3 | Generate EWB (20-25 scenarios)- Generate EWB (23,24,25 scenarios) | Regression | Jerin | Regression | Jerrin | Generate_24:Cancel exclusion without selecting any reason.-Completed Framework setup - Inprogress | Framework setup
4 | Complete "Sub-Busi Unit" and "Location" | Regression | Rajneesh |  |  | Completed "Sub-Busi Unit". | Will work on "Location" & "Add GSTIN" section.
5 | Manual Testing | Manual Testing | Aarya & Silpa |  |  | Created a new user with new master's and checked upload file as well as generate EWB. Reported Issues of the same to Praveen- Completed

## Today
# | Activities planned for today | Testing Type | Personnel | Testing Type | Personnel | Status at EOD
[6 empty] | What I accomplished today | What I will be working on tomorrow
1 | Generate Scenario- Collaborated scenario of Data upload and Generate EWB Load testing scenarios . Need to arrange test data Need to execute test run2 Analyse and send report. | Performance | Martin & Silpa | Performance | Martin | Prepared test data Executed test run2 Collected details Report preparation -in progress | Need to send report
2 | Generate EWB (1-10 scenarios) - TRA_1:On first time login user should be prompted to reset password | Regression | Aarya | Regression | Aarya | Integrating with new framework-All EWB-Inprogress | Integrating with new framework
3 | Generate EWB (20-25 scenarios)- Generate EWB (23,24,25 scenarios) Framework setup | Regression | Jerin | Regression | Jerrin | Generate EWB (Scenario 25)-Completed Framework setup -In progress | Framework setup
4 | "Location" & "Add GSTIN" section. | Regression | Rajneesh |  |  | working on "Location" | Complete Location